## Project Timeline
Centranz
PROJECT TITLE |  | Centranz |  | COMPANY NAME |  | University of Minnesota
PROJECT MANAGER |  |  |  | DATE |  | 2019-02-16
PHASE |  |  | DETAILS
|  |  |  | Saturday | Sunday |  | Monday | Tuesday |  |  | Wednesday | Thursday | END
1 | Project Conception and Initiation |  | - Project Proposal | Project Charter | [8 empty] | PROJECT END
|  |  | - Plan Review | Plan review
|  |  | -Set channels | Set Channels
2 | Project Planning |  | -Planning | Ash
|  |  | - Gantt Chart | Ash
|  |  | -Task Plan | Ash
|  |  | -Set Deliverables | Ash
3 | Project Working |  | Create Schema | Kishore
|  |  | Table ideas | Team
|  |  | Clean Data | Team
4 | Project review |  | Implement table ideas |  | Team
|  |  | Have at least 1 table created |  |  |  |  | Team
|  |  | Collaborate on tables | [5 empty] | Team
|  |  | Clean Code | [6 empty] | Team
5 | Project Submissions |  | - Report | [8 empty] | Team
|  |  | -Submission | [8 empty] | Kishore

## Deliverables
Deliverables
Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
Project scope | Create table ideas | Begin implementation of tables | Have 1 table created per person | Collaboration | Clean code and submit
Proposal | Clean data
Create tables
Create tasks for members